## Slide 1: OpenHIM Risk Assessment
A quantification of the risk profile of the RHEA interoperability layer.

## Slide 2: Overview
Methods
Results
  Present assessment
  Comparative results between April and August
Discussion
  Perceived average risks
  Issues of concern
  Evolving risk profile (April to August)
Risk Mitigation

## Slide 3: Methods
The present risk assessment has been conducted using a standards-based approach based on ISO 31000, AS/NZ 4360 and NASA’s GQM methodology
An Excel-based survey instrument was constructed
  7 Goals were assessed; for each Goal, Questions and Metrics were developed to support quantification
  For each metric, measures of risk likelihood and risk impact were captured using a 5-point Likert scale
    Likelihood (1-5): Best Case | Good | Medium | Poor | Worst Case
    Impact (1-5): Insignificant | Minor | Moderate | Major | Catestrophic
    Unknown values for likelihood or impact treated conservatively (5)
    Risk = Likelihood * Impact: Red (12-25) | Amber (5-11) | Green (1-4)
The survey instrument was completed by OpenHIM technical staff on April 8, 2012 and August 24, 2012

## Slide 4: Results
Summary Results (2012-08-24)
Result Details (2012-08-24)
Comparative Summary Results
Comparative Details (Risk Reduced)
Comparative Details (Risk Increased)

## Slide 5: Summary Results (2012-08-24)
Average & maximum risk, by Goal #

## Slide 6: Result Details (2012-08-24)
Metrics, filtered to show “RED” risks only; sorted by descending risk

## Slide 7: Comparative Summary Results
Average & maximum risk by Goal by Date – most recent shown first

## Slide 8: Comparative Details (Risk Reduced)
Comparative metric scores – most recent shown first

## Slide 9: Comparative Details (Risk Increased)
Comparative metric scores – most recent shown first

## Slide 10: Discussion
Presently, the highest perceived average risk lies in the requirements gathering processes (G1) and in the maintainability of the operating environment (G6) and the extensibility of the system once operational (G7)
The lowest perceived average risk lies in the software design documents and processes (G2) and the maintainability of the system architecture (G5)
The highest (maximum) perceived risk lies with the scalability of the system and its functionality & stability

## Slide 11: Discussion
Specific issues of concern include:
  Inability of the system to rollback to a stable state in the event of a component or system failure
  The current lack of a reference implementation
  Ambiguity regarding use cases, alignment of system requirements to business requirements and governance (sign-off) processes; ambiguity regarding subsequent implementation phases and product roadmap
  Immaturity of software testing processes, system operating procedures and performance monitoring capabilities

## Slide 12: Discussion
Overall – comparing the April and August results – the average perceived risk was reduced or stayed the same for 5 of the 7 assessed Goals
Comparing April to August, the average perceived risk increased regarding requirements gathering processes & artefacts (G1) and regarding the extensibility of the system once operational (G7); the maximum perceived risk of G1 increased slightly

## Slide 13: Discussion
Perceived risks were reduced on 6 of the 52 assessed metrics; perceived risks increased on 5 assessed metrics
4 assessed metrics improved “out of the red zone”
For 3 metrics, the perceived risk entered “into the red zone”
  Formally documenting business/clinical requirements
  Governance (sign-off) of functional requirements
  Availability of a reference / test system

## Slide 14: Risk Mitigation
Clearly define the present use cases (1.1.1)
Develop plans and processes to support change management in end-user workflows (1.1.3)
Employ rigorous documentation methods to describe business/clinical and system functional requirements (1.1.4, 1.2.2)
Relate functional to business/clinical requirements and definitively establish the degree of system “coverage” (1.3.1, 1.3.2)
Adopt a formal governance/sign-off process for system functional requirements (1.3.3)

## Slide 15: Risk Mitigation
Log and analyse software test results (3.1.5, 3.1.6)
Establish a reference implementation of the system production environment; make this environment available for testing (3.2.1, 4.5.3)
Develop orchestration capabilities in the software system; enable rollback to a stable state in the event of component or system failures (4.1.4, 4.4.1)
Develop performance monitoring “hooks” in the software system; support 3rd party monitoring products (4.3.1, 4.3.2, 6.1.5)

## Slide 16: Risk Mitigation
Cultivate redundancy in the software developer team; create a way to preserve “corporate memory” regarding software design and development practices (5.1.4)
Develop standard operating procedures for the system including setup, maintenance and code promotion procedures (6.1.3, 6.1.5)
Develop and sign-off a road map for subsequent phases of the RHEA project; align the software system’s product plan to this road map (7.1.1, 7.1.3)